## Risk Register
Risk ID | Risk Category $ | Risk Statement | Asset | Theat Source $ | Threat | Likelihood | Impact | Risk Level $ | Control | Owner | Treatment | Due Date
R-001 | Platform Security | End-of-life OS may cause vulnerabilities and unpatched exploits | Linux (CentOS 7) for web servers. | External attackers | Exploitation of unpatched OS vulnerabilities | Likely | Major | High | vulnerability scans ,WAF, SSL/TLS | IT Security | Mitigate : (Migrate to supported OS, patch mgmt)
R-002 | Platform Security | Compromise of Windows Server 2019 used for payment processing could expose cardholder data | Payment Processing Servers (Windows 2019) | Hackers, malware, ransomware | Missing EDR on servers, patch delays, admin privileges | Likely | Catastrophic | Critical | SSL/TLS, WAF | Payments Manager / IT Infra Lead | Mitigate: Deploy EDR on servers, enable centralized patch mgmt, enforce PAM/MFA

## Standards
impact |  |  | Likelihood | [9 empty] | Risk Rating Scale
Score | Impact level | Desciption | Score | Likelihood Level | Description | [7 empty] | Risk Score | Level
5 | Catastrophic | Severe financial loss, significant reputational damage, regulatory penalties, loss of customer trust | 5 | Almost Certain | Expected to occur multiple times per year | [7 empty] | 0 | Low
4 | Major | Substantial financial loss, moderate reputational damage, regulatory fines possible | 4 | Likely | Expected to occur annually | [7 empty] | 5 | Medium
3 | Moderate | Noticeable financial impact, limited reputational harm, some operational disruption | 3 | Possible | May occur within 2–3 years | [7 empty] | 10 | High
2 | Minor | Minor financial loss, minimal reputational impact, limited operational disruption | 2 | Unlikely | May occur within 3–5 years | [7 empty] | 17 | Critical
1 | Insignificant | Negligible financial/reputational impact, little or no disruption | 1 | Rare | Expected to occur multiple times per year
impact
[8 empty] | Insignificant (1) | Minor (2) | Moderate (3) | Major(4) | Catastrophic (5)
[6 empty] | Likelihood | Rare (1) | 1 | 2 | 3 | 4 | 5
[7 empty] | Unlikely (2) | 2 | 4 | 6 | 8 | 10
[7 empty] | Possible (3) | 3 | 6 | 9 | 12 | 15
[7 empty] | Likely (4) | 4 | 8 | 12 | 16 | 20
[7 empty] | Almost Certain (5) | 5 | 10 | 15 | 20 | 25