## Risk Register
Risk ID | Risk Category $ | Risk Statement | Asset | Theat Source $ | Threat | Likelihood | Impact | Risk Level $ | Control | Owner | Treatment | Due Date
R-001 | Platform Security | End-of-life OS may cause vulnerabilities and unpatched exploits | Linux (CentOS 7) for web servers. | External attackers | Exploitation of unpatched OS vulnerabilities | Likely (4) | Major (4) | High (16) | vulnerability scans ,WAF, SSL/TLS | IT Security | Mitigate : (Migrate to supported OS, patch mgmt)
R-002 | Platform Security | Compromise of Windows Server 2019 used for payment processing could expose cardholder data | Payment Processing Servers (Windows 2019) | Hackers, malware, ransomware | Missing EDR on servers, patch delays, admin privileges | Likely (4) | Catastrophic (5) | Critical (20) | SSL/TLS, WAF | Payments Manager / IT Infra Lead | Mitigate: Deploy EDR on servers, enable centralized patch mgmt, enforce PAM/MFA
R-003 | Database Security | Risk of unauthorized access or data breach in MySQL DB | MySQL 8.0 (e-commerce catalog + customer data) | Insider threat, External attackers | SQL Injection, Data exfiltration | Possible(3) | Major (4) | Medium (12) |  | DB Administrator | Mitigate: Implement strong authentication (MFA), regular database audits, SQL injection prevention measures. Additional Mitigation: Plan to separate e-commerce catalog and customer data into two separate databases by Q4 2025.

## Standerd
impact |  |  | Likelihood | [9 empty] | Risk Rating Scale
Score | Impact level | Desciption | Score | Likelihood Level | Description | [7 empty] | Risk Score | Level
5 | Catastrophic | Severe financial loss, significant reputational damage, regulatory penalties, loss of customer trust | 5 | Almost Certain | Expected to occur multiple times per year | [7 empty] | 1 – 4 | Low
4 | Major | Substantial financial loss, moderate reputational damage, regulatory fines possible | 4 | Likely | Expected to occur annually | [7 empty] | 5 – 9 | Low Med
3 | Moderate | Noticeable financial impact, limited reputational harm, some operational disruption | 3 | Possible | May occur within 2–3 years | [7 empty] | 10 – 14 | Medium
2 | Minor | Minor financial loss, minimal reputational impact, limited operational disruption | 2 | Unlikely | May occur within 3–5 years | [7 empty] | 15 – 19 | High
1 | Insignificant | Negligible financial/reputational impact, little or no disruption | 1 | Rare | Expected to occur multiple times per year | [7 empty] | 20 – 25 | Critical
impact
[8 empty] | Insignificant | Minor | Mogerate | Major | Catastrophic
[6 empty] | Likelihood | Almost Certain | Low Med | Medium | High | Critical | Critical
[7 empty] | Likely | Low | Low Med | Medium | High | Critical
[7 empty] | Possible | Low | Low Med | Medium | High | High
[7 empty] | Unlikely | Low | Low Med | Low Med | Medium | High
[7 empty] | Rare | Low | Low | Low Med | Medium | Medium