## Risk Register
Risk ID | Risk Category | Risk Statement | Asset | Threat | Vulnerabilities | Likelihood | Impact | Risk Level | Control | control Effectiveness | Residual Risk | Owner | Treatment | Due Date | ISO 27001 Control | PCI DSS Control | Residual Risk (Post Controls)
PHYS-001 | Infrastructure | Exploitation of outdated CentOS 7 web servers leading to RCE or privilege escalation. | Web Servers | Hackers, Exploit Kits | End-of-life OS, unpatched packages | Likely | Catastrophic | Critical | WAF + SSL/TLS + Daily Vulnerability Scans | Weak | High | System Admin Lead & Infrastructure | Avoid – migrate to supported platforms, enforce patch management, replace legacy components | 2025-08-30 | A.12.6.1 (Vulnerability Mgmt), A.14.2.3 (System hardening) | - | Medium
PHYS-002 | Data Security | Unauthorized access to financial transactions processed on Windows Server 2019. | Payment Processing Servers | Hackers, Malware | Weak access controls, delayed patching | Likely | Catastrophic | Critical | WAF + SSL/TLS + Daily Vulnerability Scans | Fair | Medium | Information Security Manager | Mitigate – enforce access restrictions, apply MFA, patching, endpoint protection | 2025-08-28 | A.9.1.2 (User access), A.9.2.3 (Password mgmt), A.10.1 (Crypto) | Req. 7.1 (Restrict access), Req. 8.2 (Authentication), Req. 3.4 | Low
PHYS-003 | Network Security | Unauthorized access due to weak firewall or network misconfiguration. | Routers, Switches, Firewalls | External attackers | Misconfigured rules, weak passwords | Likely | Major | High | WAF + SSL/TLS + Daily Vulnerability Scans | Fair | Medium | IT & Network Security Manager | Mitigate – harden firewall configs, enable monitoring, enforce network segmentation | 2025-08-28 | A.13.1 (Network controls), A.13.1.3 (Network segregation) | - | Medium
PHYS-004 | Insider Risk | Data leakage through phishing or malware infections on employee desktops | Employee Desktops | Malicious insiders, Malware | Weak endpoint protection, phishing | Possible | Moderate | Medium | Daily Vulnerability Scans | Weak | Medium | IT & Infrastructure | Mitigate – enforce stronger endpoint protection and user awareness | 2025-08-28 | A.12.2.1 (Anti-malware), A.7.2.2 (Awareness), A.9.2.1 (User reg) | - | Low
PHYS-005 | Availability | POS system downtime disrupting transactions. | POS Systems | Hardware failure, DoS attack | Lack of monitoring/alerting | Possible | Moderate | Medium |  | Ineffective | Medium | Business Continuity Manager | Mitigate – Regular maintenance , Redundancy for POS | 2025-08-28 | A.17.1.1 (Continuity planning), A.17.2.1 (Availability facilities) | - | Low
SW-001 | Application Security | SQL Injection on e-commerce platform leading to customer data breach. | E-commerce Platform | Hackers | Poor input validation | Likely | Catastrophic | Critical | WAF + SSL/TLS + Daily Vulnerability Scans | Fair | Medium | IT / Application Development / Security Team | Mitigate – Secure coding standards, Dev training, regular penetration testing | 2025-08-27 | A.14.2.1 (Secure development), A.14.2.8 (Testing security) | - | Medium
SW-002 | Mobile Security | Reverse engineering or API abuse in mobile app. | Mobile App | Hackers | Weak API auth, insecure storage | Possible | Moderate | Medium | SSL/TLS, WAF, Daily Vulnerability Scans | Weak | Medium | Mobile Development / App Security Team | Mitigate – API hardening, code obfuscation, stronger auth (MFA, token-based) | 2025-08-27 | A.14.2.5 (Secure system engineering), A.14.2.9 (Testing apps) | - | Medium
SW-003 | Data Security | Transaction interception or failure at payment gateway. | Digital Payment Gateway | Hackers, MITM | Weak encryption, DDoS | Likely | Major | High | SSL/TLS, WAF, Daily Vulnerability Scans | Fair | Medium | Payment Operations + Security Team | Transfer – Use PCI-compliant provider, DDoS protection | 2025-08-27 | A.10.1 (Cryptography), A.13.1 (Network controls) | Req. 3.4 (Protect PAN), Req. 4.1 (Strong crypto) | Medium
SW-004 | ERP Risk | Unauthorized access to financial records in SAP Business One. | SAP Business One | Hackers, Insiders | Weak role-based access | Possible | Moderate | Medium | Daily Vulnerability Scans | Weak | Medium | Finance/ERP Owner + IT Security | Mitigate – Strengthen RBAC, enforce least privilege, enable audit logging | 2025-08-27 | A.9.1.2 (Access provisioning), A.12.4.1 (Logging) | - | Low
SW-005 | Security Control Failure | WAF bypass through new exploit techniques. | Web Application Firewall | Hackers | Zero-day bypass methods | Possible | Major | High | WAF, SSL/TLS, Daily Vulnerability Scans | Weak | Medium | Security Team | Accept – Residual risk, vendor updates | 2025-08-27 | A.12.6.1 (Vulnerability mgmt), A.15.1.1 (Supplier monitoring) | - | Medium
SW-006 | Security Control Gaps | Vulnerability scanners missing zero-days. | Vulnerability Scanners | Hackers, Exploit Kits | Scanner limitations | Rare | Moderate | Low | Daily Vulnerability Scans | Weak | Low | Security Team | Mitigate + Accept – Continuous scanning, patch mgmt, Threat Intel monitoring | 2025-08-27 | A.12.6.1 (Vulnerability mgmt), A.16.1 (Incident mgmt) | - | Low
DB-001 | Data Security | SQL Injection attack could expose or manipulate sensitive data. | MySQL 8.0 Database | Hackers, External Attackers | Poor input validation, lack of query sanitization | Likely | Catastrophic | Critical | WAF, SSL/TLS, vulnerability scans | Weak | High | DBA + Dev Team | Mitigate – Enforce parameterized queries, periodic penetration testing | 2025-08-24 | A.14.2.5 (Secure engineering), A.14.2.9 (Testing apps) | - | Medium
DB-002 | Insider Threat | Privileged users may abuse access rights to extract or modify data. | MySQL 8.0 Database | DBAs, Developers, Admins | Excessive privileges, weak logging | Possible | Catastrophic | High | Daily Vulnerability Scans | Weak | Medium | DBA + Security Team | Mitigate – least privilege, audit logging, RBAC, encryption | 2025-08-24 | A.9.2.3 (Privileged access), A.12.4 (Logging), A.18.1.3 | - | Medium
DB-003 | Availability | Database outage caused by misconfiguration, hardware failure, or DDoS attack. | MySQL 8.0 Database | Botnets, Human Error, Hardware | Single point of failure, weak redundancy | Likely | Major | High | Daily Vulnerability Scans | Weak | Medium | DBA + IT Infrastructure | Transfer – Implement HA clustering, cloud-based failover,Daily backups | 2025-08-24 | - | Req. 9.5 (Backup media security), Req. 12.10 (IRP) | Low
DB-004 | Compliance | Non-compliance with ISO 27001 / PCI DSS due to storage of customer payment and personal data. | MySQL 8.0 Database | Regulators, Auditors | Missing PCI DSS technical controls | Likely | Major | High | Daily Vulnerability Scans | Weak | Medium | Compliance Officer + DBA + Security Team | Mitigate – Tokenization, enforce PCI DSS controls, align with ISO 27001 Annex A requirements. It is required to separate E-commerce Catalog data from Customer Data to evaluate risks and compliance obligations independently. | 2025-08-24 | A.18.1.1 (Legal requirements), A.18.1.4 (Privacy and PII), A.18.2 (Compliance reviews) | Req. 3.2 (Protect stored cardholder data), Req. 3.4 (Encryption), Req. 12.1 (Policies) | Medium
INT-001 | Data Security | Leakage of customer personal data (PII). | Customer Data | Hackers, Insiders | Weak encryption, insider access | Likely | Catastrophic | Critical | SSL/TLS, Daily Vulnerability Scans | Weak | High | Compliance & Risk Mgmt | Mitigate – MFA, DLP solutions, DB encrption,,Access control hardening | 2025-08-24 | A.9.4.1 (Access restrictions), A.10.1 (Encryption), A.18.1.4 (PII protection) | - | Medium
INT-002 | Data Security | Breach of financial data, including credit cards. | Financial Data | Hackers | Weak PCI DSS compliance | Likely | Catastrophic | Critical | SSL/TLS, Daily Vulnerability Scans | Weak | High | Compliance & Risk Mgmt | Mitigate – PCI DSS controls, tokenization,Encryption of cardholder data | 2025-08-24 | - | Req. 3.2 (Protect cardholder data), Req. 3.4 (Encryption), Req. 11.3 (Pen testing) | Medium
INT-003 | Availability / Reputation | Domain hijacking or DNS spoofing. | Domain Name | Hackers | Weak registrar protection | Unlikely | Major | Medium |  | Ineffective | Medium | Business Owners | Transfer – DNS security via registrar | 2025-08-24 | A.13.1.1 (Network segregation), A.13.2.1 (Security in network services) | - | Low
INT-004 | Reputation | Brand identity misuse, phishing sites. | Brand Identity | Hackers, Competitors | Lack of monitoring | Possible | Moderate | Medium |  | Ineffective | Medium | Business Owners | Mitigate – Brand monitoring services, takedown services | 2025-08-24 | A.16.1.7 (Mitigation of incidents), A.18.1.1 (Legal compliance) | - | Medium
HUM-001 | Insider Threat | Malicious insider leaking sensitive data. | Team Members | Malicious Insiders | Excessive access rights | Likely | Catastrophic | Critical |  | Ineffective | High | HR + Security | Mitigate – Background checks, least privilege,RBAC | 2025-08-24 | A.7.1.2 (Screening), A.9.2.3 (Privileged access), A.12.4.1 (Logging) | - | Medium
HUM-002 | Human Error | Accidental misconfiguration or data deletion. | Team Members | Employees | Lack of training, human mistakes | Possible | Moderate | Medium |  | Ineffective | Medium | HR + IT | Mitigate – Awareness training, backup policies | 2025-08-24 | A.7.2.2 (Security awareness training), A.12.3 (Backups), A.17.1 (Continuity) | - | Medium

## Standards
impact |  |  | Likelihood | [9 empty] | Risk Rating Scale |  | Effectiveness
Score | Impact level | Desciption | Score | Likelihood Level | Description | [7 empty] | Risk Score | Level | Score | Effectiveness level | Description
5 | Catastrophic | Severe financial loss, significant reputational damage, regulatory penalties, loss of customer trust | 5 | Almost Certain | Expected to occur multiple times per year | [7 empty] | 0 | Low | 1 | Excellent | Controls fully mitigate the risk
4 | Major | Substantial financial loss, moderate reputational damage, regulatory fines possible | 4 | Likely | Expected to occur annually | [7 empty] | 5 | Medium | 0.8 | Good | Controls significantly reduce risk
3 | Moderate | Noticeable financial impact, limited reputational harm, some operational disruption | 3 | Possible | May occur within 2–3 years | [7 empty] | 10 | High | 0.6 | Fair | control partially reduce risk
2 | Minor | Minor financial loss, minimal reputational impact, limited operational disruption | 2 | Unlikely | May occur within 3–5 years | [7 empty] | 17 | Critical | 0.4 | Weak | controls provide minimal reduction
1 | Insignificant | Negligible financial/reputational impact, little or no disruption | 1 | Rare | Expected to occur very rarely (once in 5–10 years) | [9 empty] | 0.2 | Ineffective | Controls provide almost no reduction
impact
[8 empty] | Insignificant (1) | Minor (2) | Moderate (3) | Major(4) | Catastrophic (5)
[6 empty] | Likelihood | Rare (1) | Low | Low | Low | Low | Medium
[7 empty] | Unlikely (2) | Low | Low | Medium | Medium | High
[7 empty] | Possible (3) | Low | Medium | Medium | High | High
[7 empty] | Likely (4) | Low | Medium | High | High | Critical
[7 empty] | Almost Certain (5) | Medium | High | High | Critical | Critical